## CLAIM_MASTER_APR_26_DRAFT
PROJ REF. | VENDOR/SUBCON | WORK DESC (Kerja) | CONTRACT VAL | CLAIM # | CLAIM AMT (RM) | STATUS | DATE SUBMIT | REMARKS/NOTA
RC-HL-01 | MajuJaya S/B | Piling works | 2500000 | 1 | 250000 | Paid | 12/03/2026 | OK
rc-hl-02 | Syarikat Ali & Sons | Kerja Tanah | RM 850k | Claim 3 | 150,000.00 | Pending | 15-Mar-26 | waiting for JUPEM surveyor
| Mega Steel Enterprise | Supply rebar | 1200000 | 2 | RM 200,000 | KIV | 2026/03/18 | harga besi naik, need VO approval
03 | Ah Chong Plumbing | Paip air dalaman |  | 1 | 50000 | bayar | early march | tolak RM500 for site clearing
RC-HL-04 | Bina Cepat Sdn. Bhd. | Concreting Level 1 | 3,450,000.00 |  | Pending QS | reject | 22/3/2026 | failed slump test, no payment
Proj_05 | Klinik Siti | Medical checkup worker | 5000 | Inv #221 | 5000 | PAID | 1 April 26 | HR department budget, not site
RC-HL-06 | Tenaga Nasional | TNB Temp supply deposit | 150000 | - | 150k | Paid | 05/04/2026 | Resit hilang, finance marah bising2
RC-HL-01 | MajuJaya S/B | Piling works (VO 1) | 125,000 | 1A | 125000 | pending | 4/4/26 | waiting PM sign off
??? | Kantin Makcik Kiah | Catering for site visit | 250 | Cash | 250 | Claim petty cash | 12 April 2026 | Boss suruh bayar dulu
TOTAL CLAIMED: